## Sheet1
Sprint | Task | Type |  | Download
Sprint 0 | Test bed setup for Devops tool
Sprint 0 | Source Control | Gitlab, Bitbucket |  | Gitlab --- https://about.gitlab.com/downloads/#centos7
Sprint 0 | CI Server & Plugins for Unit test execution result and code coverage | Jenkins,Bamboo |  | Jenkins --- http://pkg.jenkins-ci.org/redhat-stable/jenkins-2.19.1-1.1.noarch.rpm
Sprint 0 | Build tool (maven or ant or gradle) | Maven,Ant
Sprint 0 | Provisioning /Configuration management tool | Ansible
Sprint 0 | Application monitoring tool | Pingdom | mrtg monitor
Sprint 0 | Application log monitoring tool | Logstash | Elasticsearch | Kibana | Busines metrics (?) | Scope finalization (what all needs to be setup)
Sprint 0 | Deployment tool | Ansible , Bash
Sprint 0 | Branching Strategy | Git workflows;merging techniques(commands);branching techniques(git reco);
Sprint 0 | Versioning Strategy | source code; db scripts; property files
Sprint 0 | CI pipeline architecture/flow | CI for dev cycles; CI for release cycles
Sprint 0 | CD pipleline architecture/flow | dev/release
Sprint 0 | Unit testing integration strategy | check with Jayanti
Sprint 0 | Functional testing integration strategy | check with Jayanti
Sprint 0 | Provisioning/Configuration Management Framework | Groups, roles, hosts, playbook
Sprint 0 | Scope of extending application monitoring and integration | discussed in #7
Sprint 0 | Educate scrum team for CI and CD principles | best practice implementations, what should be the definition of done from scrum team members perspective
Sprint 0 | Tools installation/topology documentation | Core team ? (RISK)
Sprint 1 | Source Code migration | CI
Sprint 1 | Setup productionized version of CI tool | CI
Sprint 1 | Setup build jobs in CI tool as per branching & release strategy | CI
Sprint 1 | Setup Unit test execution in CI tool | CI
Sprint 1 | Setup notification on build success/failures | CI
Sprint 1 | Publish build artifacts | CI
Sprint 2 | Env/App Env specific runtime resources preparation | CD
Sprint 2 | Deployment scripts authoring for Binaries | CD
Sprint 2 | Deployment scripts authoring for runtime resources | CD
Sprint 2 | Deployment scripts authoring for DB changes | CD
Sprint 2 | Deployment verification | CD
Sprint 2 | CD pipeline execution/Build promotion | CD
Sprint 2 | Integrate functional testing | CD
Dashboarding of build results
Metrics

## Sheet2
Project Name | Migrated to Git | Build Jobs | Deploy Jobs | Externalized Properties | DBScripts in SCM
SportsLottery | Yes |  |  |  | TBD
TicketPrintingApp | Yes
PMS | Yes | Yes |  |  | TBD
DrawGameWeb | Yes | Yes |  |  | TBD
RMS | Yes | Yes |  |  | TBD
PCPOSAppletTicketEngine | Yes
SLEAppletTicketEngine | Yes
PrintingAppNodeServer | Yes
Flash | Yes
DGE | Yes | Yes |  |  | TBD