## SALT
S No. | SOW Activity | Type of Activity | Sprint Applicability | Project | Start Date | End Date | Effort | Status | Remarks | Pre-requisites if any | Dependancy on | Blocks
Agile Approach
1 | Set Up Sprint ZERO (0) | General | SPRINT 0 | LMS
2 | Training on Agile Scrum | General | SPRINT 0 | LMS |  |  |  | Open
3 | Scrum Master Trainings | General | SPRINT 0 | LMS |  |  |  | Open
4 | Setup Daily Stand up between Skilrock and Xebia | General | SPRINT 0 | LMS |  |  |  | Open
5 | Define Sprint 1 and 2 Line items for Implementation | General | SPRINT 0 | LMS |  |  |  | Open
6 | Discuss the Tool approach for Agile / DevOps / Test Automation (All Tools) | General | SPRINT 0 | LMS |  |  |  | Open
7 | Define Definition of Done | Agile | SPRINT 0 | LMS |  |  |  | Open
8 | Agree on Definition of Done | Agile | SPRINT 0 | LMS |  |  |  | Open
9 | Define Definition of Ready | Agile | SPRINT 0 | LMS |  |  |  | Open
10 | Agree on Definition of Ready | Agile | SPRINT 0 | LMS |  |  |  | Open
11 | Include INVEST criteria in Definition of Ready | Agile | SPRINT 0 | LMS |  |  |  | Open
12 | Agile Estimators | Agile | SPRINT 0 | LMS |  |  |  | Open
13 | Training - Planning Poker and suitable estimation techniques | Agile | SPRINT 0 | LMS |  |  |  | Open
14 | Mapping Table for Poker @ team level | Agile | SPRINT 0 | LMS |  |  |  | Open
15 | Estimation using Poker for identified project sprints | Agile | SPRINT 0 | LMS |  |  |  | Open
16 | Metrics Agreement with Skilrock | Agile | SPRINT 0 | LMS |  |  |  | Open
17 | # of stories groomed in Backlog refinement | Agile | SPRINT 0 | LMS |  |  |  | Open
18 | User Stories validated against DoR | Agile | SPRINT 0 | LMS |  |  |  | Open
19 | User Stories validated against DoD | Agile | SPRINT 0 | LMS |  |  |  | Open
20 | Reliable Estimates - % of usr stories in a sprint with the variance of more than 30% | Agile | SPRINT 0 | LMS |  |  |  | Open
21 | Reduction in number of user stories in WIP @ Sprint end – Reduction in # of Stories not delivered | Agile | SPRINT 0 | LMS |  |  |  | Open
22 | Number of Retrospective Item – Getting actioned and improved | Agile | SPRINT 0 | LMS |  |  |  | Open
23 | Derive velocity of each scrum team - at the end of sprint | Agile | SPRINT 0 | LMS |  |  |  | Open
24 | Trend charts - Velocity data | Agile | SPRINT 0 | LMS |  |  |  | Open
25 | Sprint Burndown chart | Agile | SPRINT 0 | LMS |  |  |  | Open
26 | Release Burndown chart | Agile | SPRINT 0 | LMS |  |  |  | Open
27 | Dashboards | Agile | SPRINT 0 | LMS |  |  |  | Open
28 | Daily Kanban/Scrum Board | Agile | SPRINT 0 | LMS |  |  |  | Open
29 | Scrum of Scrum Board | Agile | SPRINT 0 | LMS |  |  |  | Open
30 | Blocker Board | Agile | SPRINT 0 | LMS |  |  |  | Open
31 | Sprint Burndown | Agile | SPRINT 0 | LMS |  |  |  | Open
32 | Release Burndown | Agile | SPRINT 0 | LMS |  |  |  | Open
33 | Team Velocity | Agile | SPRINT 0 | LMS |  |  |  | Open
34 | Release Management Dashboard | Agile | SPRINT 0 | LMS |  |  |  | Open
35 | Automation of Unit Test Cases | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
36 | Selection of unit testing tools | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
37 | Educate/orient team on developing UT cases - document standards | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
38 | Introduce TDD process through Selected Tool | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
39 | Selection of code coverage analysis tool | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
40 | Static code/unit test coverage tool implementation | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
41 | Define approach for thresholds for code coverage | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
42 | Review the current coding practices | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
43 | Review the current Code as developed | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
44 | Review / Read - Current Unit Test cases - if automated | Unit Test Automation / TDD | SPRINT 0 | LMS |  |  |  | Open
45 | Technical Debt and Refactoring | Technical Debt / Refactoring | SPRINT 0 | LMS |  |  |  | Open
46 | Identify technical debt in the code | Technical Debt / Refactoring | SPRINT 0 | LMS |  |  |  | Open
47 | Document the technical debt examples | Technical Debt / Refactoring | SPRINT 0 | LMS |  |  |  | Open
48 | Functional Test Automation | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
49 | Application KT and algorithm understanding. | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
50 | Authorization and Access Privileges | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
51 | Setting up of evironments and infrastructure for various environments | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
52 | identifying modules and features underscope | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
53 | Publish test strategy (Automation frameworks, tools and coverage - (processes, policies and tools)) | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
54 | Define Functional Test Automation Training Plan | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
55 | Train on Functional Test Automation | Functional Test Automation | SPRINT 0 | LMS |  |  |  | Open
56 | Generic Elements of DevOps | DevOps | SPRINT 0 | LMS |  |  |  | Open
57 | Test bed setup for Devops tool | DevOps | SPRINT 0 | LMS |  |  |  | Open
58 | Source Control | DevOps | SPRINT 0 | LMS |  |  |  | Open
59 | CI Server & Plugins for Unit test execution result and code coverage | DevOps | SPRINT 0 | LMS |  |  |  | Open
60 | Build tool (maven or ant or gradle) | DevOps | SPRINT 0 | LMS |  |  |  | Open
61 | Provisioning /Configuration management tool | DevOps | SPRINT 0 | LMS |  |  |  | Open
62 | Application monitoring tool | DevOps | SPRINT 0 | LMS |  |  |  | Open
63 | Application log monitoring tool | DevOps | SPRINT 0 | LMS |  |  |  | Open
64 | Deployment tool | DevOps | SPRINT 0 | LMS |  |  |  | Open
65 | Define and Agree Branching Strategy | DevOps | SPRINT 0 | LMS |  |  |  | Open
66 | Define and Agree Versioning Strategy | DevOps | SPRINT 0 | LMS |  |  |  | Open
67 | Define CI pipeline architecture/flow | DevOps | SPRINT 0 | LMS |  |  |  | Open
68 | Define CD pipleline architecture/flow | DevOps | SPRINT 0 | LMS |  |  |  | Open
69 | Define Unit testing integration strategy | DevOps | SPRINT 0 | LMS |  |  |  | Open
70 | Define Functional testing integration strategy | DevOps | SPRINT 0 | LMS |  |  |  | Open
71 | Provisioning/Configuration Management Framework | DevOps | SPRINT 0 | LMS |  |  |  | Open
72 | Scope of extending application monitoring and integration | DevOps | SPRINT 0 | LMS |  |  |  | Open
73 | Educate scrum team for CI and CD principles | DevOps | SPRINT 0 | LMS |  |  |  | Open
74 | Tools installation/topology documentation | DevOps | SPRINT 0 | LMS |  |  |  | Open
75 | Getting Ready for Launching the Sprint 1 | General | SPRINT 0 | LMS |  |  |  | Open
76 | Team is available | General | SPRINT 0 | LMS |  |  |  | Open
77 | Team is trained on Agile Scrum Concepts | Agile | SPRINT 0 | LMS |  |  |  | Open
78 | User stories documented in respective tool or XLS (to start with) | Agile | SPRINT 0 | LMS |  |  |  | Open
79 | User Story Slicing / Splitting | Agile | SPRINT 0 | LMS |  |  |  | Open
80 | Implement Product Backlog Refinement | Agile | SPRINT 0 | LMS |  |  |  | Open
81 | Identifying Non-Technical User Stories (NFRs) - If any | Agile | SPRINT 0 | LMS |  |  |  | Open
82 | Creation of Release Backlog - Epics, Estimates and User stories including mapping | Agile | SPRINT 0 | LMS |  |  |  | Open
83 | Apply DoR on the User Stories for Sprint 1 | Agile | SPRINT 0 | LMS |  |  |  | Open
84 | Sprint 1 @ Skilrock | General | SPRINT 1 | LMS |  |  |  | Open
85 | Sprint Planning Meeting | Agile | SPRINT 1 | LMS |  |  |  | Open
86 | Daily Scrum through Selected Tool | Agile | SPRINT 1 | LMS |  |  |  | Open
87 | Sprint Review | Agile | SPRINT 1 | LMS |  |  |  | Open
88 | Sprint Retrospective | Agile | SPRINT 1 | LMS |  |  |  | Open
89 | Product Backlog Refinement - For Sprint 2 | Agile | SPRINT 1 | LMS |  |  |  | Open
90 | Agile ceremonies effectiveness | Agile | SPRINT 1 | LMS |  |  |  | Open
91 | Sprint Planning | Agile | SPRINT 1 | LMS |  |  |  | Open
92 | Backlog Grooming | Agile | SPRINT 1 | LMS |  |  |  | Open
93 | Daily Scrum | Agile | SPRINT 1 | LMS |  |  |  | Open
94 | Sprint Review | Agile | SPRINT 1 | LMS |  |  |  | Open
95 | Sprint Retrospective | Agile | SPRINT 1 | LMS |  |  |  | Open
96 | Time Boxed Ceremonies - Time adherence report | Agile | SPRINT 1 | LMS |  |  |  | Open
97 | Application of Definition of Done - User stories acceptance | Agile | SPRINT 1 | LMS |  |  |  | Open | Release 18.1, Sprint 2
98 | User Story Slicing / Splitting | Agile | SPRINT 1 | LMS |  |  |  | Open
99 | Test Automation (Unit Testing) | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
100 | Implement selected tools for unit testing (Hand Holding support for 5 developers) | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
101 | Include UT process in Definition of Done along with coverage analysis | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
102 | Unit test coverage report - MIS | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
103 | Build failure reasons and owner (Unit testing) - Report | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
104 | Integrate with CI Process - If CI is ready | Unit Test Automation / TDD | SPRINT 1 | LMS |  |  |  | Open
105 | Functional Test Automation | Functional Test Automation | SPRINT 1 | LMS |  |  |  | Open
106 | Trainings on Selenium, appium, cucumber, JUnit, Maven (Depends on Selection and Finalization of Tools) | Functional Test Automation | SPRINT 1 | LMS |  |  |  | Open
107 | Machine Setup for automation team | Functional Test Automation | SPRINT 1 | LMS |  |  |  | Open
108 | Development of automation framework | Functional Test Automation | SPRINT 1 | LMS |  |  |  | Open
109 | Define approaches to test data preparation | Functional Test Automation | SPRINT 1 | LMS |  |  |  | Open
110 | Continuous Integration (CI) | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
111 | Source Code migration | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
112 | Setup productionized version of CI tool | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
113 | Setup build jobs in CI tool as per branching & release strategy | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
114 | Setup Unit test execution in CI tool | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
115 | Setup notification on build success/failures | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
116 | Publish build artifacts | Continuous Integration (CI) | SPRINT 1 | LMS |  |  |  | Open
117 | Sprint 2 | Agile | SPRINT 2 | LMS |  |  |  | Open
118 | Sprint Planning Meeting | Agile | SPRINT 2 | LMS |  |  |  | Open
119 | Daily Scrum through Selected Tool | Agile | SPRINT 2 | LMS |  |  |  | Open
120 | Sprint Review | Agile | SPRINT 2 | LMS |  |  |  | Open
121 | Sprint Retrospective | Agile | SPRINT 2 | LMS |  |  |  | Open
122 | Product Backlog Refinement - For Sprint 3 | Agile | SPRINT 2 | LMS |  |  |  | Open
123 | Agile ceremonies effectiveness | Agile | SPRINT 2 | LMS |  |  |  | Open
124 | Sprint Planning | Agile | SPRINT 2 | LMS |  |  |  | Open | Sprint 5 Onwards
125 | Backlog Grooming | Agile | SPRINT 2 | LMS |  |  |  | Open
126 | Daily Scrum | Agile | SPRINT 2 | LMS |  |  |  | Open
127 | Sprint Review | Agile | SPRINT 2 | LMS |  |  |  | Open
128 | Sprint Retrospective | Agile | SPRINT 2 | LMS |  |  |  | Open
129 | Time Boxed Ceremonies - Time adherence report | Agile | SPRINT 2 | LMS |  |  |  | Open
130 | Application of Definition of Done - User stories acceptance | Agile | SPRINT 2 | LMS |  |  |  | Open
131 | User Story Slicing / Splitting | Agile | SPRINT 2 | LMS |  |  |  | Open | Sprint 6 onwards
132 | Test Automation (Unit Testing) | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
133 | Implement selected tools for unit testing (Hand Holding support for 5 developers) | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
134 | Include UT process in Definition of Done along with coverage analysis | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
135 | Unit test coverage report - MIS | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
136 | Build failure reasons and owner (Unit testing) - Report | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
137 | Integrate with CI Process - If CI is ready | Unit Test Automation / TDD | SPRINT 2 | LMS |  |  |  | Open
138 | Technical Debt and Refactoring | Technical Debt / Refactoring | SPRINT 2 | LMS |  |  |  | Open
139 | Coverage of technical debt in estimation/agile process | Technical Debt / Refactoring | SPRINT 2 | LMS |  |  |  | Open
140 | Demonstrate and train - How to identify technical debt | Technical Debt / Refactoring | SPRINT 2 | LMS |  |  |  | Open
141 | Prepare SME on code refactoring skills | Technical Debt / Refactoring | SPRINT 2 | LMS |  |  |  | Open
142 | Functional Test Automation | Functional Test Automation | SPRINT 2 | LMS |  |  |  | Open
143 | Team training and implementation of BDD (Hand Holding Support) | Functional Test Automation | SPRINT 2 | LMS |  |  |  | Open
144 | Giving assignments and reviewing them | Functional Test Automation | SPRINT 2 | LMS |  |  |  | Open
145 | Adding test cases for better test coverage | Functional Test Automation | SPRINT 2 | LMS |  |  |  | Open
147 | Conitnuous Delivery (CD) | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
148 | Env/App Env specific runtime resources preparation | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
149 | Deployment scripts authoring for Binaries | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
150 | Deployment scripts authoring for runtime resources | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
151 | Deployment scripts authoring for DB changes | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
152 | Deployment verification | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
153 | CD pipeline execution/Build promotion | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
154 | Integrate functional testing | Conitnuous Delivery (CD) | SPRINT 2 | LMS |  |  |  | Open
155 | [7 empty] | Open
156 | Code Management | [6 empty] | Open
157 | Code Review Management process | [6 empty] | Open
158 | Define code review process | [6 empty] | Open
159 | Define Coding Standards | [6 empty] | Open
160 | Define best practices for coding standards | [6 empty] | Open
161 | Include code review process in DoD | [6 empty] | Open
162 | Code Review - Observation/defect logging template | [6 empty] | Open
163 | Demonstrate code review process | [6 empty] | Open
164 | Implement code review and defects management tool | [6 empty] | Open
165 | Publish MIS - Code Review through tools/manual process | [6 empty] | Open
Open
| Planning Poker Session for the teams. | [6 empty] | Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
In Progress
Done
Blocked